## Metadata
Output | Compliance Matrix
Generated | 2026-08-04 08:48 UTC
Rows | 7
Project | Civic Center HVAC Retrofit
Organization | Acme Infrastructure Group
Run | #12

## Compliance Matrix
Requirement | Category | Mandatory | Owner | Status | Action Needed | Risk If Missing | Due Date | Source Document | Source Page | Source Snippet | Confidence | Human Review Required
Acknowledge Addenda 1-3 on bid form | Submission | TRUE | Proposal Lead | Ready | Verify checkboxes before upload | Bid may be rejected as nonresponsive | Jan 26 12:00 PM | Bid Form.pdf | 2 | Bidder acknowledges receipt of all addenda | 0.94 | TRUE
Submit 5% bid bond with current Power of Attorney | Bonding | TRUE | Contracts | Review | Confirm surety and POA date | Bid bond defect can disqualify the bid | Jan 25 2:00 PM | Instructions to Bidders.pdf | 18 | Bid security must include Power of Attorney | 0.89 | TRUE
Provide ACORD certificate naming City as additional insured | Insurance | TRUE | Contracts | Needs confirmation | Confirm endorsement wording from carrier | Insurance package may be incomplete | Jan 24 10:00 AM | Addendum 2.pdf | 14 | City must be listed as additional insured | 0.86 | TRUE
Confirm payment terms Net 45 and 5% retainage | Financial | FALSE | Finance | Review | Validate cash-flow impact before approval | Mobilization cash flow may be pressured | Jan 25 5:00 PM | General Conditions.pdf | 37 | Owner may withhold 5% retainage until acceptance | 0.77 | TRUE
Liquidated damages: $1,500 per calendar day | Financial risk | FALSE | Legal | Review | Confirm acceptable exposure and schedule buffer | Delay exposure could erode margin | Jan 25 5:00 PM | General Conditions.pdf | 42 | Contractor shall pay $1,500 per calendar day | 0.82 | TRUE
Provide two municipal HVAC references over $5M | Reference match | TRUE | Operations | Ready | Attach Westside Library and County Annex references | Scoring weakness if references are not comparable | Jan 26 12:00 PM | Evaluation Criteria.pdf | 9 | Submit two similar municipal retrofit references | 0.91 | FALSE
Submit signed non-collusion affidavit | Forms | TRUE | Proposal Lead | Not started | Collect signature and notarization | Mandatory form gap before submission | Jan 26 12:00 PM | Forms Package.pdf | 4 | Non-collusion affidavit must be signed | 0.93 | TRUE